## Slide 1
MODULE 2.5
Developing the procurement plan
For project managers responsible for procurement decisions
1
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan

## Slide 2
What you will be able to do
2.5-1 | L13
1
Differentiate a procurement plan from a project plan by scope and purpose
2
Identify the 8 components of a procurement plan and their role
3
Select the appropriate contract type given project constraints
2
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
By the end of this module, you'll be able to do three things. First, you'll differentiate a procurement plan from a project plan. Second, you'll identify the eight components every procurement plan needs. And third, you'll select the right contract type for a given project.
VISUAL/GRAPHIC DESCRIPTION:
Three objectives listed with numbered badges.
INTERACTION & DEV NOTES:
No interaction. Click Next to continue.

## Slide 3
You already use a project plan
2.5-2 | L01
Before we talk about procurement plans, let's anchor to something familiar.
● A project plan covers scope, timeline, resources, and deliverables
● It answers: what are we building, and when?
● Every PM creates one — it's the backbone of project execution
3
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
You already work with project plans every day. A project plan covers scope, timeline, resources, and deliverables. It answers the question: what are we building, and when will it be done?
VISUAL/GRAPHIC DESCRIPTION:
Text slide with three dash bullets on dark background.
INTERACTION & DEV NOTES:
No interaction. Click Next to continue.

## Slide 4
What is a procurement plan
2.5-3 | L03
Visual: procurement plan as a subset document that feeds into the project plan
A different question
A procurement plan answers: how will we buy, and from whom?
● Defines how purchases will be managed across the project
● Covers vendor selection, contract type, and delivery timing
● Lives alongside the project plan — not inside it
4
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
A procurement plan answers a different question: not what are we building, but how will we buy what we need? It defines how purchases will be managed, what contract types you'll use, and how you'll select vendors.
VISUAL/GRAPHIC DESCRIPTION:
Left: diagram showing procurement plan as a parallel document to the project plan, with arrows showing how procurement feeds into project timeline. Right: three key bullets.
INTERACTION & DEV NOTES:
No interaction. Click Next to continue.

## Slide 5
Project plan vs procurement plan
2.5-4 | L01
Two documents, two questions, one project.
● Project plan asks: WHAT are we building and WHEN?
● Procurement plan asks: HOW do we buy and FROM WHOM?
● Project plan owns scope and schedule — procurement plan owns commercial strategy
5
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Here's the key contrast. Your project plan asks what and when. Your procurement plan asks how and from whom. The project plan owns scope and schedule. The procurement plan owns commercial strategy — vendor selection, contract structure, and risk allocation.
VISUAL/GRAPHIC DESCRIPTION:
Three bullet points with contrasting pairs. Each bullet highlights the scope boundary between the two documents.
INTERACTION & DEV NOTES:
No interaction. Click Next to continue.

## Slide 6
Three phases of a procurement plan
2.5-5 | L01
Before we explore all eight components, here's how they organize.
● Define — what to buy (objectives, scope, method)
● Execute — how to buy (contract type, evaluation, risk)
● Govern — who decides (schedule, governance, approvals)
6
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
A procurement plan has eight components, but don't worry — they group into three phases. Define: what are we buying. Execute: how are we buying it. Govern: who makes the decisions. This framework will help you keep track as we explore each component.
VISUAL/GRAPHIC DESCRIPTION:
Three dash bullets, each representing a phase with 2-3 component names in parentheses.
INTERACTION & DEV NOTES:
No interaction. Click Next to continue.

## Slide 7
Explore each component
2.5-6 | L12
Click each component to learn more. Visit all eight to continue.
01
Objectives and criteria
02
Scope and packaging
03
Procurement method
04
Contract type
05
Evaluation approach
06
Risk and contingency
07
Schedule and milestones
08
Governance and approvals
7
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Now let's explore each of the eight components. Click on any component to open it. You'll need to visit all eight before you can move on.
VISUAL/GRAPHIC DESCRIPTION:
Eight horizontal bars stacked vertically, each with a number badge and component name.
INTERACTION & DEV NOTES:
L12 menu hub. Learner clicks each bar to open a popup. Next button disabled until all 8 are visited. Visited bars show a green checkmark.

## Slide 8
Explore each component
2.5-6-01 | Pop-up on anchor
01
Objectives and criteria
✕
Tie every criterion back to a sponsor-owned success measure.
✓ Clear measurable targets aligned to sponsor expectations
✓ Evaluation criteria weighted by strategic priority
✓ Acceptance thresholds agreed with the steering group
8
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at objectives and criteria. Clear measurable targets aligned to sponsor expectations Evaluation criteria weighted by strategic priority Acceptance thresholds agreed with the steering group Remember: tie every criterion back to a sponsor-owned success measure.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 1: Objectives and criteria. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 1.

## Slide 9
Explore each component
2.5-6-02 | Pop-up on anchor
02
Scope and packaging
✕
Packaging is your first risk allocation decision — get it right before vendors are involved.
✓ Decide single-package vs multi-package procurement
✓ Balance integration risk against vendor leverage
✓ Map each package to a delivery milestone
9
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at scope and packaging. Decide single-package vs multi-package procurement Balance integration risk against vendor leverage Map each package to a delivery milestone Remember: packaging is your first risk allocation decision — get it right before vendors are involved.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 2: Scope and packaging. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 2.

## Slide 10
Explore each component
2.5-6-03 | Pop-up on anchor
03
Procurement method
✕
Match the method to the market — don't default to open tender for every package.
✓ Open tender: maximum competition, higher admin effort
✓ Restricted tender: pre-qualified shortlist, faster
✓ Direct appointment: speed, but must justify sole-source
10
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at procurement method. Open tender: maximum competition, higher admin effort Restricted tender: pre-qualified shortlist, faster Direct appointment: speed, but must justify sole-source Remember: match the method to the market — don't default to open tender for every package.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 3: Procurement method. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 3.

## Slide 11
Explore each component
2.5-6-04 | Pop-up on anchor
04
Contract type
✕
Contract type is the single biggest risk-allocation lever in the plan.
✓ Fixed-price: risk sits with the vendor, less flexibility for changes
✓ Time-and-materials: flexibility for the buyer, risk on cost overruns
✓ Hybrid (capped T&M): shared risk, caps protect the buyer
11
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at contract type. Fixed-price: risk sits with the vendor, less flexibility for changes Time-and-materials: flexibility for the buyer, risk on cost overruns Hybrid (capped T&M): shared risk, caps protect the buyer Remember: contract type is the single biggest risk-allocation lever in the plan.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 4: Contract type. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 4.

## Slide 12
Explore each component
2.5-6-05 | Pop-up on anchor
05
Evaluation approach
✕
Weight criteria before you see proposals — not after.
✓ Technical merit: does the solution meet requirements?
✓ Price competitiveness: is the cost reasonable for the market?
✓ Risk profile: what could go wrong with this vendor?
✓ Past performance: has this vendor delivered similar work?
12
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at evaluation approach. Technical merit: does the solution meet requirements? Price competitiveness: is the cost reasonable for the market? Risk profile: what could go wrong with this vendor? Past performance: has this vendor delivered similar work? Remember: weight criteria before you see proposals — not after.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 5: Evaluation approach. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 5.

## Slide 13
Explore each component
2.5-6-06 | Pop-up on anchor
06
Risk and contingency
✕
Risk allocation happens in the contract — if it's not written down, you own it.
✓ Identify procurement-specific risks (vendor insolvency, supply chain disruption)
✓ Assign risk to the party best positioned to manage it
✓ Build contingency into timeline and budget — not just cost
13
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at risk and contingency. Identify procurement-specific risks (vendor insolvency, supply chain disruption) Assign risk to the party best positioned to manage it Build contingency into timeline and budget — not just cost Remember: risk allocation happens in the contract — if it's not written down, you own it.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 6: Risk and contingency. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 6.

## Slide 14
Explore each component
2.5-6-07 | Pop-up on anchor
07
Schedule and milestones
✕
Procurement delay is the #1 cause of project schedule slip in complex programs.
✓ Map procurement timeline to project critical path
✓ Build in lead times for tender, evaluation, and mobilization
✓ Identify dependencies between packages
14
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at schedule and milestones. Map procurement timeline to project critical path Build in lead times for tender, evaluation, and mobilization Identify dependencies between packages Remember: procurement delay is the #1 cause of project schedule slip in complex programs.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 7: Schedule and milestones. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 7.

## Slide 15
Explore each component
2.5-6-08 | Pop-up on anchor
08
Governance and approvals
✕
Clear governance prevents the 'who approved this?' conversation six months in.
✓ Define approval authority levels (who signs what value)
✓ Establish the evaluation panel composition
✓ Set escalation path for disputes and variations
15
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's look at governance and approvals. Define approval authority levels (who signs what value) Establish the evaluation panel composition Set escalation path for disputes and variations Remember: clear governance prevents the 'who approved this?' conversation six months in.
VISUAL/GRAPHIC DESCRIPTION:
Pop-up panel over the menu hub. Component 8: Governance and approvals. Key message at top, bullets below.
INTERACTION & DEV NOTES:
Pop-up overlay on anchor slide 2.5-6. X button closes and returns to anchor with checkmark on bar 8.

## Slide 16
Explore each component
2.5-6-v | L12 — Visited
01
Objectives and criteria
✓
02
Scope and packaging
✓
03
Procurement method
✓
04
Contract type
✓
05
Evaluation approach
✓
06
Risk and contingency
✓
07
Schedule and milestones
✓
08
Governance and approvals
✓
16
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VISUAL/GRAPHIC DESCRIPTION:
All 8 bars show green checkmarks. Continue button active.
INTERACTION & DEV NOTES:
All tiles visited. Next button now enabled.

## Slide 17
Knowledge check
2.5-7a | L09
You're managing a construction project with a well-defined scope, a fixed deadline, and an experienced vendor pool. Which contract type best fits this situation?
○ A. Time-and-materials — maximum flexibility for scope changes
○ B. Fixed-price — risk transferred to vendor, scope is locked
○ C. Capped T&M — shared risk with a cost ceiling
○ D. Cost-plus — vendor reimbursed for all costs plus a fee
Submit
17
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Time to check your understanding. Read the scenario and select the contract type that best fits.
VISUAL/GRAPHIC DESCRIPTION:
MCQ with 4 options. Submit button at bottom.
INTERACTION & DEV NOTES:
L09 MCQ. Learner selects one option, then clicks Submit. Next is disabled until submitted.

## Slide 18
Knowledge check
2.5-7b | L09 — Feedback
You're managing a construction project with a well-defined scope, a fixed deadline, and an experienced vendor pool. Which contract type best fits this situation?
○ A. Time-and-materials — maximum flexibility for scope changes
◉ B. Fixed-price — risk transferred to vendor, scope is locked
○ C. Capped T&M — shared risk with a cost ceiling
○ D. Cost-plus — vendor reimbursed for all costs plus a fee
✓ CORRECT
Fixed-price is the right choice here. The scope is well-defined and the deadline is fixed — that means scope changes are unlikely, so transferring delivery risk to the vendor makes sense. The experienced vendor pool means vendors can price accurately.
✗ INCORRECT
With a well-defined scope and fixed deadline, fixed-price is the strongest fit. T&M gives flexibility you don't need here, and cost-plus removes the vendor's incentive to control costs. Remember: match the contract type to the project's risk profile.
Continue
18
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's see how you did.
FEEDBACK — CORRECT:
Fixed-price is the right choice. Well-defined scope plus fixed deadline means scope changes are unlikely.
FEEDBACK — INCORRECT:
Fixed-price was the better fit here. T&M gives flexibility you don't need, and cost-plus removes cost control incentive.
DEV NOTES:
Left 2/3 shows the question with the learner's selection marked. Right 1/3 shows feedback panel (green for correct, red for incorrect). Score recorded via cmi.core.score.raw.

## Slide 19
Key takeaways
2.5-8 | L14
● A procurement plan answers 'how will we buy?' — distinct from the project plan's 'what and when?'
● Eight components group into three phases: Define, Execute, Govern
● Contract type is the biggest risk-allocation lever — match it to scope certainty and timeline pressure
Finish module
19
12 March 2026
Internal use only | Module 2.5 — Developing the procurement plan
Notes: VOICEOVER:
Let's recap. A procurement plan answers how will we buy — that's separate from your project plan. The eight components fall into three phases: define, execute, and govern. And contract type is your single biggest lever for allocating risk.
VISUAL/GRAPHIC DESCRIPTION:
Three takeaway cards with yellow left border. Finish button at bottom.
INTERACTION & DEV NOTES:
L14 summary. On entry, triggers cmi.core.lesson_status = 'completed'. Finish button calls LMSFinish.